## README
ApexPredict — Sprint S1 Engineering Backlog (Frontend + Backend)
Version 1.0 · 2026-06-07 · Sprint Tue 2026-06-09 → Mon 2026-06-22 · 54 points · 3 epics · 15 stories
Sheets:
Stories — one row per user story, Fibonacci-pointed.
Story Detail — CONTEXT, ACCEPTANCE CRITERIA, DEPENDENCIES & RISKS, DEFINITION OF READY checklist side-by-side.
Tasks — atomic engineering tasks under each story.
Capacity — sprint goal, capacity check, demo plan.
Import notes:
Jira CSV — map 'Story ID' → External ID; 'Parent Epic' → Epic Link; 'Points' → Story Points.
Linear CSV — use Epic + Story hierarchy; 'Points' → estimate.
ClickUp — import each Epic as a list, Stories as items, Tasks as subtasks.
Sprint Goal:
By end of S1, a real user can sign up, log in, manage account + RG preferences,
subscribe via Paystack (test/stub), and view a per-fixture prediction page with
bookmaker odds comparison. Pick ledger auto-settles on results.
Guardrails (carry from S0):
• No win-rate language. Calibrated probability + edge only.
• No live vendor API calls (Paystack/Smile ID/Sportmonks/Odds API/Upstash/Resend).
• Migrations: prisma migrate dev --create-only. SRE applies manually.
• No push to main; PRs off develop.
• Quality gate: typecheck + lint + test + e2e smoke must pass.
Out of scope this sprint:
Onboarding wizard, Dashboard rewrite, Methodology calibration plot, Referrals, Soft-suspend worker,
Google OAuth client REGISTRATION (PM action). All deferred to later sprints.

## Stories
Story ID | Parent Epic | Title | Points | Owner role(s) | Branch | Status
A2 | EPIC-A | Sessions list with revoke | 3 | 1 BE + 1 FE | feat/account-sessions | Committed
A3 | EPIC-A | Responsible-gaming controls UI | 5 | 1 BE + 1 FE + counsel sign-off | feat/account-rg-controls | Committed
A5 | EPIC-A | Google login button (account linking) | 2 | 1 FE + 1 BE | feat/auth-google-button | Committed
B1 | EPIC-B | Billing provider adapter interface | 3 | 1 BE | feat/billing-provider-iface | Committed
B2 | EPIC-B | Checkout API + page (server-driven) | 5 | 1 BE + 1 FE | feat/billing-checkout | Committed
B3 | EPIC-B | Billing thanks page with state polling | 2 | 1 FE | feat/billing-thanks | Committed
B4 | EPIC-B | Paystack webhook handler (idempotent) | 5 | 1 BE | feat/billing-webhook | Committed
B5 | EPIC-B | Cancel-at-period-end (API + UI) | 3 | 1 BE + 1 FE | feat/billing-cancel | Committed
B7 | EPIC-B | Webhook replay CLI for QA + support | 2 | 1 BE | feat/billing-replay-cli | Committed
C1 | EPIC-C | Match detail page rewrite (server component) | 8 | 1 BE + 1 FE | feat/match-detail-rewrite | Committed
C2 | EPIC-C | Value-Bet chip + tooltip | 2 | 1 FE | feat/value-bet-chip | Committed
C3 | EPIC-C | Kelly Stake calculator (Pro-gated) | 3 | 1 FE + 1 BE (entitlements) | feat/kelly-calculator | Committed
C4 | EPIC-C | Bookmaker deeplink + affiliate tracking | 3 | 1 BE + 1 FE | feat/affiliate-deeplinks | Committed
C5 | EPIC-C | Bookmaker model + seed | 3 | 1 BE | feat/bookmaker-model | Committed
C6 | EPIC-C | UserPick CRUD + auto-settle on result | 5 | 1 BE + 1 FE | feat/user-picks | Committed

## Story Detail
Story ID | Parent Epic | Title | Points | Owner role(s) | Branch | CONTEXT | ACCEPTANCE CRITERIA | DEPENDENCIES & RISKS | DEFINITION OF READY
A2 | EPIC-A | Sessions list with revoke | 3 | 1 BE + 1 FE | feat/account-sessions | Auth.js v5 writes a Session row per device. Today users have no way to see or revoke them. We need this for hygiene AND so a self-excluded user can forcibly log out everywhere. | • /account shows 'Active sessions' with device label, region, createdAt, current-session marker. • Each non-current row has Revoke → DELETE /api/account/sessions/[id]; bulk DELETE /api/account/sessions revokes everything except current. • Revoked sessions return 401 on next request → bounce to /login. • Every revoke writes AuditLog action=session.revoke. • Keyboard-navigable; accessible label. • Tests: revoke own (401 next req); foreign session returns 404 (not 403, anti-enum); bulk leaves current intact. | Depends on: S0 Session model + auth.ts (Done). Blocks: A4 absorbed (bulk revoke needed for forced logout). Risk: Auth.js v5 token rotation could flicker 'current' detection — read cookie once per render. Risk: UA parsing fuzzy — use allowlist regex, not heavy library; fall back to 'Unknown device'. | ☐ AC reviewed and unambiguous ☐ Session table fields confirmed against S0 schema ☐ UA-parser approach decided (allowlist regex, not library) and approved ☐ Reviewer assigned (default: BE reviewer) ☐ Mock fixture for ≥3 sessions prepared in e2e/_helpers/sessions.ts
A3 | EPIC-A | Responsible-gaming controls UI | 5 | 1 BE + 1 FE + counsel sign-off | feat/account-rg-controls | S0 shipped User.rgFlags Json + assertNotSuspended helper. No UI yet. RG self-exclusion is NLRC's most-scrutinized control and a prereq for any paid release. | • /account shows 3 RG controls: self-exclude (24h/7d/30d/permanent — 3-step modal w/ 'I UNDERSTAND' typed confirmation, irreversible within window), cool-off (1-14 days, reversible), advisory deposit cap (NGN, advisory only). • Server enforcement: rgFlags.selfExcludedUntil > now → <Suspended> banner on picks index, match detail, dashboard, notifications opt-in. • AuditLog entries: rg.selfExclude.start, rg.selfExclude.reject, rg.coolOff.start, rg.advisoryCap.set. • Copy matches compliance footer; includes 18+ line; no win-rate language. • A11y: focus trap, ESC at step 1, SR announces step transitions, axe passes. | Depends on: S0 User.rgFlags (Done), assertNotSuspended (Done), lib/audit.ts (Done). Blocks: A4 (absorbed), E07-S2 (in S1 master prompt). Risk: counsel copy review may slow merge → ship w/ eng-lead reviewed copy, mark PR needs-counsel-review, follow-up issue. Risk: 'permanent' is irreversible (no admin override here — S4 ticket). Risk: self-exclude email must be sent SYNCHRONOUSLY by the API, not a worker (to avoid re-trigger). | ☐ Copy reviewed in PR by engineering lead ☐ 3-step modal flow sketched in ticket comment, text per step in ticket ☐ User.rgFlags JSON shape documented in ticket ☐ assertNotSuspended return shape confirmed (JSX banner) ☐ Reviewer assigned (BE + design for modal a11y)
A5 | EPIC-A | Google login button (account linking) | 2 | 1 FE + 1 BE | feat/auth-google-button | S0 shipped the Auth.js Google provider config. No button yet. ~30% of NG mobile users prefer Google. Linking-by-email prevents duplicate accounts. | • /login and /signup show 'Continue with Google' above email form. • Click → signIn('google', { redirectTo: '/dashboard' }). • Existing User by email → link new Account (no duplicate User). • Google users get emailVerifiedAt = Google's email_verified ts. • Locale preserved across OAuth round-trip. • Mocked Playwright spec asserts button + flow + locale stickiness. • When AUTH_GOOGLE_ID is empty → render 'coming soon' placeholder (never crash). | Depends on: S0 auth.ts Google provider (Done). Blocks: nothing in this sprint. Risk: redirect behavior on locale-prefixed routes — test against next-intl + Auth.js v5 docs. Risk: email_verified=false on Google side → reject with 400 + friendly UI (do not link). | ☐ AUTH_GOOGLE_ID / SECRET env var names confirmed against auth.ts ☐ Placeholder copy reviewed ☐ Reviewer assigned
B1 | EPIC-B | Billing provider adapter interface | 3 | 1 BE | feat/billing-provider-iface | Clean abstraction so Paystack today + Flutterwave later both plug into the same call sites. Foundation for the entire epic — lands first. | • lib/billing/provider.ts exports BillingProvider with getCheckoutUrl, verifyWebhookSignature, parseEvent. • getActiveProvider() factory reads BILLING_PROVIDER env (default paystack). • PaystackProvider: live mode when PAYSTACK_SECRET_KEY_TEST set, stub mode otherwise (returns /dev/billing-stub URL). • FlutterwaveProvider: throw-only stub. • verifyWebhookSignature: HMAC-SHA512 hex digest vs x-paystack-signature header. 100% branch coverage. • Fixture tests/billing/__fixtures__/paystack-charge-success.json parses cleanly. | Depends on: nothing inside epic. Blocks: B2, B4, B5, B7. Risk: webhook signature spec could change — pin Paystack docs URL in ticket and recheck at start-of-sprint. | ☐ Paystack docs URL pinned in ticket ☐ Interface signature reviewed by B2 developer (consumer agrees) ☐ Fixture JSON path + content agreed ☐ Reviewer assigned
B2 | EPIC-B | Checkout API + page (server-driven) | 5 | 1 BE + 1 FE | feat/billing-checkout | Path from user clicking Subscribe to Paystack-hosted form must be single click. Server action mints idempotency key + 302-redirects. | • POST /api/billing/checkout: auth-required, validates tier, mints idempotency key, stores in KV 10min TTL, calls getActiveProvider(). • Concurrent dupes (same user+tier within 10min) return cached URL. • KV unreachable → skip caching, Sentry warning, do NOT reject. • /billing/checkout?tier=… server component → 302 to authorizationUrl. • Stub mode: dev-banner + 'Continue (simulated)' that POSTs a fake webhook. • E2E passes stub-mode flow. | Depends on: B1. Blocks: B3, B4. Risk: Vercel server-side redirect() behavior under cookies — verify in preview. Risk: KV outage policy — feature flag BILLING_IDEMPOTENCY_ENFORCED, default false initially. | ☐ B1 merged or branch local ☐ Stub-mode 'Continue (simulated)' UX reviewed by product (eng lead can stand in) ☐ KV outage policy agreed: warn + proceed, not reject ☐ Reviewer assigned
B3 | EPIC-B | Billing thanks page with state polling | 2 | 1 FE | feat/billing-thanks | After Paystack redirects with ?reference=, our Subscription row is updated by the webhook, not the redirect. Thanks page polls until status flips to active, with timeout fallback. | • /billing/thanks?reference=<ref> calls GET /api/billing/subscription on mount. • If active → success copy + CTA to /dashboard. • Otherwise poll: every 1s for first 5s, then every 2s up to 30s. • At 30s without active → fallback: 'We're still processing your payment. We'll email you when it's done.' • Polling continues in background after fallback; 'Refresh status' button always visible. • ?simulate=true (dev-only) triggers stub webhook then resumes polling. • Cleanup on unmount via AbortController. | Depends on: B2 (thanks redirect is the consumer), B4 (webhook flips status). Blocks: nothing. Risk: bad networks — keep polling in background after showing fallback. Risk: SSR — entire page is client-side after initial 'loading' SSR fallback. | ☐ B2 + B4 branches available for integration test ☐ Copy reviewed ☐ Reviewer assigned
B4 | EPIC-B | Paystack webhook handler (idempotent) | 5 | 1 BE | feat/billing-webhook | Webhook is canonical source of truth. Paystack replays events. Persist every received event in WebhookDelivery keyed on eventId. | • POST /api/billing/webhook/paystack reads raw body, verifies signature → 401 on mismatch. • Look up WebhookDelivery by eventId — if exists, return 200 {replayed:true}, no side effect. • Otherwise persist WebhookDelivery + route to handler. • Event handlers (idempotent): subscription.create/disable, invoice.create/payment_failed, charge.success/failed. • Per-event AuditLog entries with eventId + userId + post-update Subscription fields. • Prisma WebhookDelivery model w/ eventId unique constraint, migration SQL only. • Unit tests: each event type, replay, tampered signature. | Depends on: B1. Blocks: B3 (state polling), B5 (cancel needs currentPeriodEnd from invoice.create). Risk: out-of-order events — handlers use find-or-create on Subscription by (providerCustomer, providerSub). Risk: dunning emails not sent here (enqueue audit only) — actual sending in a later sprint. Risk: secret key = webhook signing key — document rotation in PR body. | ☐ B1 merged or branch local ☐ WebhookDelivery Prisma shape drafted in ticket ☐ 6 event fixtures created under tests/billing/__fixtures__/ ☐ Reviewer assigned
B5 | EPIC-B | Cancel-at-period-end (API + UI) | 3 | 1 BE + 1 FE | feat/billing-cancel | Users must cancel without losing access during the paid period. Industry standard cancel-at-period-end: keep entitlement until currentPeriodEnd, then drop to FREE. | • POST /api/billing/cancel → Subscription.cancelAt = currentPeriodEnd. Audit billing.cancel.scheduled. • DELETE /api/billing/cancel → clears cancelAt (un-cancel). • /account/billing renders subscription state; banner 'Subscription ends on <date>' when cancelAt set; Un-cancel button. • Cancel button → 2-step confirmation modal explaining what happens. • Entitlement middleware: reads Subscription.status + cancelAt; tier reflects paid until cancelAt passes, then FREE. • Unit tests: cancel sets cancelAt, un-cancel clears, passing period end flips tier. | Depends on: B4. Blocks: nothing. Risk: clock drift Paystack ↔ server — accept 5min drift in 'in past' check. Risk: legacy yearly plans with null currentPeriodEnd — fall back to 'contact support'. | ☐ B4 merged or branch local ☐ Confirmation modal copy reviewed ☐ Reviewer assigned
B7 | EPIC-B | Webhook replay CLI for QA + support | 2 | 1 BE | feat/billing-replay-cli | Support engineers need to replay or simulate Paystack events without going through Paystack. Small TS script posts canned event JSON with valid signature. | • scripts/billing-replay.ts: --fixture <path>, --url <url>, --dry-run. • Computes HMAC-SHA512 signature using PAYSTACK_SECRET_KEY_TEST. • Posts; prints response status + JSON. • 4 fixtures under scripts/fixtures/paystack-*.json: charge.success, subscription.create, invoice.create, invoice.payment_failed. • Hard-errors if NODE_ENV === 'production'. • docs/runbooks/billing-incident-response.md w/ 3 example invocations. | Depends on: B1 (signature helper), B4 (webhook route). Blocks: nothing. Risk: footgun in prod — hard-error on NODE_ENV=production. | ☐ B1 + B4 branches local ☐ Runbook outline agreed ☐ Reviewer assigned
C1 | EPIC-C | Match detail page rewrite (server component) | 8 | 1 BE + 1 FE | feat/match-detail-rewrite | Most-viewed page after predictions index, and the one that converts free → paid. Today thin. Rewrite surfaces live odds, model probability + edge, calibrated confidence, ¼-Kelly (Pro), explainable narrative, JSON-LD SportsEvent. | • /predictions/[matchId] is a server component fetching Fixture+Competition+Teams+latest PredictionSnapshot+Odds[]+FixtureEnrichment. • Sections: header, score/kickoff card, model breakdown (3 markets w/ best odds + edge chips), confidence bar, Kelly (Pro), narrative, bookmaker deeplinks, methodology link. • JSON-LD SportsEvent in <head> via lib/seo/json-ld.ts. • OG image route still works. • Empty states: missing snapshot, empty odds, signed-out user. • LCP < 2.5s on mid-3G Lighthouse profile. Only deeplink click is client-side. • All copy approved language. | Depends on: C2 (chip), C3 (Kelly), C4 (deeplinks), C5 (Bookmaker). Blocks: C6 (save-pick button lives here). Risk: narrative is auto-boilerplate today — render verbatim, don't block on quality (S2 ticket). Risk: bundle weight — keep under 80kb gzipped; server components aggressively. Risk: existing route may have hand-baked tests — port or replace cleanly. | ☐ Mockup / wireframe attached (sketch fine) ☐ Section → dependent-story map acknowledged (C2/C3/C4/C5) ☐ Existing JSON-LD helper reviewed ☐ LCP budget agreed ☐ Reviewer assigned (senior FE)
C2 | EPIC-C | Value-Bet chip + tooltip | 2 | 1 FE | feat/value-bet-chip | Reusable +EV badge. Used on predictions index, match detail, dashboard, Telegram (later). Centralizing here makes it consistent everywhere. | • components/match/ValueBetChip.tsx accepts { edgePoints, market }. • Renders 'Value +X.X% on <market label>'. • Hover/focus tooltip explains edge meaning + disclaimer (no win-rate). • Tooltip a11y: keyboard focus, ESC dismiss, SR reads on focus. • Renders nothing if edgePoints < 3. • Visual matches tailwind tokens. | Depends on: nothing. Blocks: C1. Risk: tooltip copy must avoid win-rate language. | ☐ Existing ValueBetChip diff plan agreed (extend, don't replace) ☐ Tooltip lib decided (Radix Tooltip preferred — already in deps) ☐ Reviewer assigned
C3 | EPIC-C | Kelly Stake calculator (Pro-gated) | 3 | 1 FE + 1 BE (entitlements) | feat/kelly-calculator | Bankroll discipline tool for Pro tier. Surfaces on match detail. ¼-Kelly stake suggestion given bankroll + model probability + best price. | • components/match/KellyCalculator.tsx client component. Inputs: bankroll (NGN, per-user localStorage), modelProbability (read-only), bookPrice (read-only). • Formula: kellyFraction = (p*b − (1-p))/b where b = price-1, p = modelProbability. ¼-Kelly = kellyFraction * 0.25 * bankroll. If <=0 → 'Model does not favor this market — stake = 0.' • Hidden if entitlementsFor(user).kelly === false. • Inline 'How does this work?' expander: max 1 paragraph + disclaimer. • Unit-test 6 hand-computed cases. | Depends on: lib/entitlements.ts (Done). Blocks: nothing. Risk: bankroll in localStorage must be keyed per-user; clear on logout. Risk: Kelly suggests staking when model is wrong — explainer copy must frame as conservative ceiling, not recommendation. | ☐ Formula verified against external reference (e.g., Wikipedia Kelly) ☐ Pro entitlement key 'kelly' confirmed against entitlementsFor matrix ☐ Copy reviewed ☐ Reviewer assigned
C4 | EPIC-C | Bookmaker deeplink + affiliate tracking | 3 | 1 BE + 1 FE | feat/affiliate-deeplinks | Affiliate revenue depends on outbound clicks tagged w/ our code. /go/:bookCode logs AffiliateClick and 302s with the bookmaker's affiliate URL template populated. | • Prisma AffiliateClick model: id, userId (nullable), bookCode, fixtureId (nullable), market (nullable), ipHash, uaHash, createdAt. Index (bookCode, createdAt). • GET /go/:bookCode?fixtureId=&market= writes row + 302 to Bookmaker.affiliateUrlTemplate w/ {{vars}} substituted. • IP/UA hashed via lib/hash.ts (HMAC). • Match detail page buttons link to /go/<bookCode>?fixtureId=…&market=… (server-rendered href). • Signed-out users still write row w/ userId=null. • lib/affiliate/template.ts safely substitutes + allowlists destination URLs (anti open-redirect). | Depends on: C5 (Bookmaker model — affiliateUrlTemplate lives there). Blocks: C1. Risk: open-redirect if bookCode user-controlled — lookup Bookmaker, reject unknown. Risk: privacy — use existing HMAC helper, not raw IP/UA. | ☐ C5 merged or branch local ☐ Affiliate URL template format agreed ({{var}} syntax) ☐ Reviewer assigned
C5 | EPIC-C | Bookmaker model + seed | 3 | 1 BE | feat/bookmaker-model | Today bookmaker data is static JSON. Move to Bookmaker table for editor updates without redeploy and so AffiliateClick references real rows. | • Prisma Bookmaker model: id, code (unique slug), displayName, regions (Json), affiliateUrlTemplate, affiliateNetwork, defaultUtm (Json), logoUrl, isActive, timestamps. • Migration SQL only. • packages/db/seed/bookmakers.ts seeds 6 operators (sportybet, bet9ja, onexbet, betking, msport, pinnacle) w/ placeholder templates. • lib/data/get-bookmakers.ts reads DB w/ KV cache (60s TTL), in-memory 5min fallback if KV unreachable. • Existing bookmakers.json deleted; consumers migrated to helper. • getBookmakersForRegion(region) returns only active books in that region. | Depends on: nothing. Blocks: C1, C4. Risk: existing JSON shape — keep helper return shape compatible w/ consumers to minimize diff. Risk: KV outage → fall back to in-memory cache, never block render. | ☐ Existing bookmakers.json shape reviewed; target schema agreed ☐ Seed list (6 operators + regions) finalized in ticket ☐ Reviewer assigned
C6 | EPIC-C | UserPick CRUD + auto-settle on result | 5 | 1 BE + 1 FE | feat/user-picks | S0 shipped UserPick model. Wire the API + UI to create picks from match detail and auto-settle them when FixtureResult.upsert runs. | • POST /api/picks: auth, rate-limit 10/hr/user. Creates UserPick with result=PENDING. • GET /api/picks: current user's picks, ordered desc, paginated 20/page. • PATCH /api/picks/[id]: update stake/bookCode/price while PENDING. After settle: 409. • DELETE /api/picks/[id]: only while PENDING. • Auto-settle: on FixtureResult.upsert in daily-refresh, iterate PENDING UserPick rows for that fixture, flip result to WIN/LOSS/VOID, set settledAt. • 'Save this pick' modal on match detail: pre-filled recommended market, default stake ₦1,000. • AuditLog: pick.create/update/delete/settle. • E2E: user saves pick → /account/picks shows it → settle sim moves it to WIN/LOSS. | Depends on: S0 UserPick model (Done), C1 (match detail hosts button). Blocks: future dashboard rewrite. Risk: daily-refresh route maxDuration — cap settlement at 1000 picks/fixture/run; warn on overflow. Risk: POSTPONED matches → result=VOID; ensure cron handles this branch. | ☐ UserPick fields confirmed ☐ Settlement decision tree documented in ticket (WIN/LOSS/VOID by Fixture.status + result market) ☐ Reviewer assigned

## Tasks
Task ID | Story ID | Parent Epic | Subject | Description
A2-T1 | A2 | EPIC-A | API: DELETE /api/account/sessions/[id] | Auth-required; delete row keyed by id+userId match. Audit session.revoke. 204/404.
A2-T2 | A2 | EPIC-A | API: DELETE /api/account/sessions (bulk) | Bulk-revoke all sessions except request cookie's. Audit session.revoke.bulk.
A2-T3 | A2 | EPIC-A | UA-to-label utility | lib/sessions/device-label.ts w/ allowlist + 'Unknown device' fallback. 10 canned UAs unit-tested.
A2-T4 | A2 | EPIC-A | Server component: sessions list | RSC in account/page.tsx fetching sessions; marks current.
A2-T5 | A2 | EPIC-A | Client wrapper: revoke button | Calls API; toast on success; refreshes list. Loading + error states.
A2-T6 | A2 | EPIC-A | E2E: revoke flow | Playwright spec: add 2nd session via helper, revoke it, assert gone.
A3-T1 | A3 | EPIC-A | API: POST /api/account/self-exclude | Validate window enum; set rgFlags.selfExcludedUntil; 409 if already active. Audit. Immediate email.
A3-T2 | A3 | EPIC-A | API: cool-off start/cancel | POST for set (1-14 days); DELETE for cancel within window. Audit.
A3-T3 | A3 | EPIC-A | API: POST /api/account/advisory-cap | Numeric + currency; persist rgFlags.advisoryCap; audit.
A3-T4 | A3 | EPIC-A | RGControls section component | Server-rendered shell + client islands.
A3-T5 | A3 | EPIC-A | 3-step self-exclude modal | Focus-trapped; ESC at step 1 only; SR step transitions.
A3-T6 | A3 | EPIC-A | Suppression suite wired into picks UI | <Suspended> on /predictions, match detail, dashboard, onboarding.
A3-T7 | A3 | EPIC-A | Self-exclude transactional email | React Email template via Resend, synchronous from API. Compliance footer.
A3-T8 | A3 | EPIC-A | Unit + integration tests | Happy + reject-during-window. axe on modal.
A5-T1 | A5 | EPIC-A | UI: Google button component | Server-rendered link; a11y; locale-aware redirect.
A5-T2 | A5 | EPIC-A | Linking logic | signIn callback: lookup User by email, attach Account; reject email_verified=false.
A5-T3 | A5 | EPIC-A | Placeholder fallback | Render 'coming soon' disabled state when AUTH_GOOGLE_ID unset.
A5-T4 | A5 | EPIC-A | E2E spec | Mocked OAuth; session + locale stickiness.
B1-T1 | B1 | EPIC-B | BillingProvider interface + types | TS types in lib/billing/provider.ts. Discriminated union BillingEvent.
B1-T2 | B1 | EPIC-B | PaystackProvider impl (live + stub) | Stub mode when env keys absent; live when set.
B1-T3 | B1 | EPIC-B | FlutterwaveProvider stub | Throw-only impl.
B1-T4 | B1 | EPIC-B | getActiveProvider() factory | Read BILLING_PROVIDER env; default paystack.
B1-T5 | B1 | EPIC-B | Signature verify + event parse tests | 6 event fixtures + tampered-body negative.
B1-T6 | B1 | EPIC-B | .env.example updates | BILLING_PROVIDER, PAYSTACK_PUBLIC_KEY_TEST, PAYSTACK_SECRET_KEY_TEST.
B2-T1 | B2 | EPIC-B | API route POST /api/billing/checkout | Auth + tier validation + KV idempotency + provider call.
B2-T2 | B2 | EPIC-B | Stub-mode simulate webhook trigger | POST /api/billing/_dev/simulate-paystack — dev only.
B2-T3 | B2 | EPIC-B | Server component /billing/checkout | Reads tier, calls API, redirects. Dev banner in stub mode.
B2-T4 | B2 | EPIC-B | Idempotency feature flag | BILLING_IDEMPOTENCY_ENFORCED documented + tested.
B2-T5 | B2 | EPIC-B | E2E spec (stub mode) | Click Subscribe → stub banner → Continue (simulated) → webhook → subscription row.
B3-T1 | B3 | EPIC-B | API: GET /api/billing/subscription | Returns current user's Subscription JSON.
B3-T2 | B3 | EPIC-B | Thanks page component | Polling + UI states (loading/success/fallback).
B3-T3 | B3 | EPIC-B | Refresh status button | Manual re-poll trigger.
B3-T4 | B3 | EPIC-B | Dev-mode ?simulate=true flow | Triggers stub webhook then waits.
B4-T1 | B4 | EPIC-B | Prisma migration: WebhookDelivery | id, provider, eventId (unique), eventType, payload Json, processedAt, createdAt.
B4-T2 | B4 | EPIC-B | Webhook route | Raw-body; signature; replay check; event router.
B4-T3 | B4 | EPIC-B | Per-event handlers | Idempotent updates; find-or-create on Subscription.
B4-T4 | B4 | EPIC-B | Audit hooks | One AuditLog row per event.
B4-T5 | B4 | EPIC-B | Test fixtures + tests | Replay; signature mismatch; per-event happy.
B5-T1 | B5 | EPIC-B | POST /api/billing/cancel | Sets cancelAt; audit.
B5-T2 | B5 | EPIC-B | DELETE /api/billing/cancel | Clears cancelAt; audit.
B5-T3 | B5 | EPIC-B | Account billing section | Subscription state + cancel/un-cancel.
B5-T4 | B5 | EPIC-B | Confirmation modal | Accessible 2-step.
B5-T5 | B5 | EPIC-B | Entitlement-aware fallback | FREE if Subscription cancelled past cancelAt.
B5-T6 | B5 | EPIC-B | Tests | Unit (clock logic) + E2E (cancel + un-cancel UX).
B7-T1 | B7 | EPIC-B | CLI script | Argv; signature; fetch; print.
B7-T2 | B7 | EPIC-B | Fixtures (×4) | Real-looking Paystack payloads.
B7-T3 | B7 | EPIC-B | Prod guard | Hard-error if NODE_ENV=production.
B7-T4 | B7 | EPIC-B | Runbook | docs/runbooks/billing-incident-response.md.
C1-T1 | C1 | EPIC-C | Data-fetching server util | lib/data/get-match-detail.ts joined object.
C1-T2 | C1 | EPIC-C | Page shell + header | /predictions/[matchId]/page.tsx rewrite. RSC.
C1-T3 | C1 | EPIC-C | Model breakdown section | Probability bars + edge chips. MatchCard tokens.
C1-T4 | C1 | EPIC-C | Confidence bar component | Reuse components/match/ConfidenceBar.tsx.
C1-T5 | C1 | EPIC-C | JSON-LD SportsEvent | Helper + integration.
C1-T6 | C1 | EPIC-C | Empty states | Awaiting-model + no-odds branches.
C1-T7 | C1 | EPIC-C | E2E spec | Section renders + SR navigation check.
C2-T1 | C2 | EPIC-C | Extend ValueBetChip | Accept edgePoints + market; suppress < 3.
C2-T2 | C2 | EPIC-C | Tooltip integration | Radix Tooltip; accessible.
C2-T3 | C2 | EPIC-C | Storybook story / visual regression | Verify hover + focus.
C2-T4 | C2 | EPIC-C | Unit test | Renders nothing below threshold; correct copy above.
C3-T1 | C3 | EPIC-C | Calculator component | Math + inputs + outputs + edges.
C3-T2 | C3 | EPIC-C | Entitlement gating | Server check on kelly; client unmount if false.
C3-T3 | C3 | EPIC-C | Per-user bankroll persistence | localStorage keyed by userId; clear on logout.
C3-T4 | C3 | EPIC-C | Inline 'How does this work?' | Collapsible.
C3-T5 | C3 | EPIC-C | Tests | 6 math cases + gating + persistence.
C4-T1 | C4 | EPIC-C | Prisma AffiliateClick + migration | Schema + index.
C4-T2 | C4 | EPIC-C | /go/[bookCode] route | Validate; lookup template; substitute; redirect.
C4-T3 | C4 | EPIC-C | Template substitution helper | Safe replacement; allowlist check.
C4-T4 | C4 | EPIC-C | Match detail page buttons | Render server-side hrefs.
C4-T5 | C4 | EPIC-C | Tests | Open-redirect attempt → 404; valid → row + 302.
C5-T1 | C5 | EPIC-C | Prisma Bookmaker model + migration | Schema + indices on (code, isActive).
C5-T2 | C5 | EPIC-C | Seed script | 6 operators; idempotent upsert by code.
C5-T3 | C5 | EPIC-C | lib/data/get-bookmakers.ts | DB-backed + KV cache + in-memory fallback.
C5-T4 | C5 | EPIC-C | Migrate consumers | Replace bookmakers.json reads.
C5-T5 | C5 | EPIC-C | Tests | Region filter; KV outage fallback; seed idempotency.
C6-T1 | C6 | EPIC-C | API routes | Create/list/update/delete w/ auth + rate-limit + audit.
C6-T2 | C6 | EPIC-C | Settlement hook | Extend daily-refresh settlement to UserPick rows.
C6-T3 | C6 | EPIC-C | Save-pick modal on match detail | Pre-filled; submits; toast.
C6-T4 | C6 | EPIC-C | Basic picks list /account/picks | List to verify data flow. No styling polish.
C6-T5 | C6 | EPIC-C | E2E spec | End-to-end save + settle simulation.

## Capacity
Sprint S1 — Capacity & Demo
Tue 2026-06-09 → Mon 2026-06-22 · 4 engineers (2 BE + 2 FE)
Engineer | Likely picks (rebalance at sprint planning)
BE-1 (14 pts) | B1 (3), B4 (5), C6 backend half (3), C5 (3)
BE-2 (14 pts) | B2 backend (3), B5 backend (2), C4 backend (2), A3 backend (3), A2 backend (2), B7 (2)
FE-1 (14 pts) | C1 (8), C2 (2), C3 (3), A5 (1)
FE-2 (14 pts) | C6 FE half (2), B2 FE (2), B3 (2), B5 FE (1), A2 FE (1), A3 FE (2), C4 FE (1), A5 (1)
Sprint Review Demo Plan (Mon 2026-06-22)
1. AUTH + ACCOUNT — fresh signup → verify email → log in via Google (mocked) → view sessions → set advisory cap → self-exclude → see <Suspended> on /predictions.
2. CHECKOUT — click Subscribe Monthly → Paystack stub banner → Continue (simulated) → webhook fires → /billing/thanks resolves to active → entitlement reflects in UI.
3. MATCH DETAIL — open fixture → model breakdown + value-bet chip on strongest market + Kelly (Pro) + bookmaker deeplinks (302 to placeholder) → save pick → see in /account/picks.
4. SETTLE SIM — trigger daily-refresh manually → saved pick flips WIN/LOSS.
If any of these four is red, the sprint is not green.
Stretch (pull only with eng-lead approval)
D2 — Preferences API (2 pts) — User.preferences Json + GET/PATCH /api/account/preferences.
D3 — Picks recommendation by preference (2 pts) — feed filtered by user.preferences.leagues.
Out of scope this sprint
Onboarding wizard (D1) — needs design pass.
Dashboard rewrite — depends on UserPick volume; lands after C6 matures.
Methodology calibration plot — depends on backtest data accumulating.
Referrals UI + grant job — defer until paid-conversion baseline exists.
Soft-suspend worker (E02-S3-T4) — backend cron concern, pairs w/ QStash decomp.
Google OAuth client REGISTRATION — human PM action; code wiring lives in A5.