## README
ApexPredict — Engineering Backlog (importable)
Version 1.0 · 2026-06-04 · Kickoff Tuesday 2026-06-09 · Launch Mon 2026-08-04
Sheets in this workbook:
Backlog — all tasks, one per row. Import this into Linear / Jira / ClickUp.
EpicSummary — epic-level rollup with story + task counts and estimate totals.
SprintCapacity — capacity model per sprint with totals.
Legend — sprint colors, estimates legend.
Columns explained:
Epic ID / Epic Name — high-level area.
Story ID / Title — coherent user-visible outcome.
Task ID / Subject — atomic engineering ticket.
Sprint — S0 / S1 / S2 / S3 / S4 / S4-Launch.
Estimate — XS<=2h · S<=1d · M<=3d · L<=5d · XL=1-2w.
Owner role — BE, FE, ML, SRE, QA, PM, DES, Counsel, DPO.
Description — what to do.
Deliverables — what should exist when done.
Acceptance criteria — testable pass conditions.
Dependencies — comma-separated task IDs that must complete first.
Import notes:
Jira CSV: map 'Task ID' -> Custom field 'External ID'; 'Story Title' -> Parent (Story).
Linear CSV: use Epic + Story + Issue hierarchy by grouping on Epic ID + Story ID.
ClickUp: import each Epic as a list, Stories as folders, Tasks as items.
Do not edit the schema columns; add new columns to the right if needed.

## Backlog
Epic ID | Epic Name | Story ID | Story Title | Task ID | Task Subject | Sprint | Estimate | Owner role | Description | Deliverables | Acceptance Criteria | Dependencies
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T1 | Stand up shared secret vault | S0 | S | SRE | Provision 1Password Business or Doppler workspace 'apexpredict-prod'. Vaults: bootstrap, dev, staging, prod. Add CTO + 2 engineers + SRE. | Vault link in docs/runbooks/secrets.md; member list captured in PM tool; audit log enabled. | All teammates can authenticate; no secrets stored outside the vault; export disabled.
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T2 | Open Paystack test account, fetch keys | S0 | XS | PM | Register Web Forx Technology Ltd on Paystack. Stay in test mode. Generate PAYSTACK_PUBLIC_KEY_TEST, PAYSTACK_SECRET_KEY_TEST, webhook signing secret. | Keys in 'bootstrap' vault; webhook endpoint URL agreed and documented. | Test transaction succeeds end-to-end via cURL using the secret key. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T3 | Open Smile ID sandbox | S0 | XS | PM | Register on Smile ID; create sandbox partner ID + API key. Capture pricing + free-test cap. | Keys in vault; pricing note in docs/runbooks/kyc.md. | Sample NIN verification call succeeds in sandbox. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T4 | Open Sportmonks trial + The Odds API free | S0 | XS | BE | Create accounts, capture tokens, confirm league coverage. Sportmonks trial is 14 days — track expiry. | Tokens in vault; coverage notes in docs/runbooks/data-providers.md. | Sample fixture pull works; NPFL coverage gap explicitly noted with fallback plan. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T5 | Open Upstash (Redis + QStash), Axiom, PostHog free | S0 | XS | SRE | Create projects; capture REST/HTTP tokens. Document quotas (Redis 10k req/d; QStash 500 msg/d). | Tokens in vault; quotas in runbook. | Sample SET/GET works in Redis; sample QStash message dispatched. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T6 | Cloudflare zone for apexpredict.ai | S0 | S | SRE | Move DNS to Cloudflare (free). Enable DNSSEC. Add SPF/DKIM/DMARC for Resend mailing domain. | DNS records committed to docs/runbooks/dns.md. | mail-tester.com score >= 9; DNSSEC chain validates. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T7 | Billing alerts on every vendor | S0 | S | SRE | Configure 80%-of-quota or budget alerts for: Vercel, Neon, Upstash, Odds API, Sportmonks, Smile ID, Resend, Sentry, Axiom. | Screenshot evidence in docs/runbooks/cost-alerts.md. | Alert delivered to cto@webforx.global AND sre@webforx.global from at least 2 vendors as proof. | E00-S1-T1
E00 | Prep & Foundations | E00-S1 | Provider accounts opened & secrets vaulted | E00-S1-T8 | Document rotation cadence | S0 | S | SRE | Quarterly secret rotation calendar; HMAC primary/secondary plan covering HASH_SECRET_PRIMARY/SECONDARY. | docs/runbooks/secrets.md with table: secret -> owner -> next rotation -> last rotation. | Calendar entries created in shared calendar with 7-day reminder.
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T1 | Activate CI workflow on PR + push | S0 | S | SRE | Switch .github/workflows/ci.yml from workflow_dispatch to PR + push triggers. Cache pnpm store keyed on lockfile. | Updated YAML; first green run on a sample PR. | Jobs: install -> typecheck -> lint -> unit -> e2e:smoke run on every PR within 6 min.
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T2 | Add CodeQL SAST job | S0 | S | SRE | Add github/codeql-action init + analyze steps for javascript-typescript. | Workflow file; CodeQL alerts visible in Security tab. | PR with intentional eval() fails CI with a CodeQL high severity. | E00-S2-T1
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T3 | Add gitleaks secret scanner | S0 | XS | SRE | Add gitleaks/gitleaks-action@v2. Tune .gitleaks.toml to allow .env.example. | Workflow + config file. | Commit with a fake AWS key triggers failure; .env.example does not. | E00-S2-T1
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T4 | Add Playwright e2e:smoke step | S0 | S | QA | Add an e2e:smoke script running e2e/00-smoke.spec.ts that asserts: landing renders, waitlist returns 202 for an empty body, /api/health returns 200. | New spec + workflow step with `playwright install --with-deps chromium`. | Smoke job completes in <90s; red on intentional breakage; required before merge. | E00-S2-T1
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T5 | Mirror CI to Forgejo Actions | S0 | S | SRE | Port the same workflow into .forgejo/workflows/ci.yaml. | YAML committed; first green run. | Forgejo PRs run the same jobs as GitHub; required before merge. | E00-S2-T1
E00 | Prep & Foundations | E00-S2 | CI/CD activated, branch protection enforced | E00-S2-T6 | Branch protection on main | S0 | XS | SRE | In Forgejo and GitHub: require PR, 1 reviewer, all status checks pass, no force push. | Settings screenshots in docs/runbooks/branch-protection.md. | Attempt to push direct to main fails for non-admin user. | E00-S2-T5
E00 | Prep & Foundations | E00-S3 | Legal & compliance engagement started | E00-S3-T1 | Retain Nigerian gaming counsel | S0 | M | PM | Shortlist 3 firms; pick one; sign retainer. | Signed PDF in legal vault; firm contact in PM tool. | First call scheduled within S0.
E00 | Prep & Foundations | E00-S3 | Legal & compliance engagement started | E00-S3-T2 | Submit NLRC opinion-letter brief | S0 | S | Counsel | Draft + file: 'Is a non-bookmaker AI-prediction + affiliate platform a regulated activity under NLRC, and if so under which licence category?' | Filed brief; expected response window noted. | Acknowledgement of receipt logged. | E00-S3-T1
E00 | Prep & Foundations | E00-S3 | Legal & compliance engagement started | E00-S3-T3 | NDPA Data Controller registration | S0 | S | DPO | File registration via NDPC portal for Web Forx Technology Ltd. | Acknowledgement receipt in legal vault. | Receipt within 7 days; followup ticket if not.
E00 | Prep & Foundations | E00-S3 | Legal & compliance engagement started | E00-S3-T4 | Draft advertising-standards posture | S0 | S | PM | One-page internal doc: prohibited claims, required disclosures, RG copy. | docs/compliance/advertising-posture.md. | Reviewer (Counsel) signs off in writing. | E00-S3-T1
E00 | Prep & Foundations | E00-S4 | Stale lockfile cleared, dev env validated | E00-S4-T1 | Clear .git/index.lock on shared dev machine | S0 | XS | SRE | Stale .git/index.lock blocks committing. Manually remove. | Verified clean status on the shared dev machine. | git status shows clean tree.
E00 | Prep & Foundations | E00-S4 | Stale lockfile cleared, dev env validated | E00-S4-T2 | Verify fresh-clone build | S0 | XS | BE | On a fresh clone: pnpm install && pnpm -F @apexpredix/web build succeeds with Node 22. | Updated README with any required corepack / Node pin. | Two engineers independently confirm.
E00 | Prep & Foundations | E00-S4 | Stale lockfile cleared, dev env validated | E00-S4-T3 | Provision shared Neon dev DB (free tier) | S0 | S | SRE | Single shared dev branch in S0; per-engineer branches enabled in S1. | Connection string in vault; pgcli verified. | Prisma migrations apply cleanly. | E00-S1-T1
E00 | Prep & Foundations | E00-S4 | Stale lockfile cleared, dev env validated | E00-S4-T4 | Write CONTRIBUTING.md | S0 | S | PM | Branching model, Conventional Commits convention, PR template, review SLA (24h). | CONTRIBUTING.md + .github/pull_request_template.md committed. | First PR after merge follows the template.
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T1 | Add Auth.js v5 + Prisma adapter + argon2 | S1 | M | BE | pnpm add next-auth@beta @auth/prisma-adapter argon2. Wire app/api/auth/[...nextauth]/route.ts. | Route + provider config; argon2id work factor >= 19 MiB / iterations 2 / parallelism 1. | Login + signup flows produce valid sessions in dev. | E00-S4-T3
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T2 | Extend Prisma schema with User/Account/Session | S1 | M | BE | Conform to Auth.js v5 + add locale, region, kycStatus, rgFlags Json, disabledAt. Rename existing VerificationToken to AuthVerificationToken. | Migration applied; generated client; back-compat verified. | Existing WaitlistSignup rows are not affected. | E01-S1-T1
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T3 | Signup + verify-email flow | S1 | M | BE | /[locale]/signup -> POST /api/auth/signup -> email via Resend -> /[locale]/verify-email?token=... | Pages, route, email template (verify); anti-enumeration response shape. | Signup with existing email returns same 202 as new email. | E01-S1-T1, E01-S1-T2
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T4 | Login + lockout | S1 | S | BE | /[locale]/login with credentials + magic-link. 5-strike lockout per (emailHash,ipHash) in KV 15-min sliding. | Page + route + KV helper. | 6th failed attempt within 15 min returns 429; success resets counter. | E01-S1-T1
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T5 | Forgot / reset password | S1 | S | BE | Email a tokenised reset link. Reset invalidates all sessions for that user. | Pages + routes + email template. | Token expires 60 min; reuse rejected. | E01-S1-T3
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T6 | AuditLog model + logAudit helper | S1 | S | BE | AuditLog model; logAudit(actor, action, target, meta) helper. Wire into every auth event. | Model + helper + tests; wired into every auth.* path. | Failed signup writes auth.signup.fail with reason; success writes auth.signup.success. | E01-S1-T2
E01 | Identity & Subscription Foundation | E01-S1 | Email/password + magic-link auth | E01-S1-T7 | E2E auth tests | S1 | S | QA | Playwright: signup -> verify -> login -> lockout -> reset -> re-login. Mock Resend in CI. | e2e/03-auth.spec.ts; runs in CI. | All 6 steps pass; intentional regressions caught. | E01-S1-T1..6
E01 | Identity & Subscription Foundation | E01-S2 | Google OAuth (one-tap) | E01-S2-T1 | Register Google OAuth client | S1 | XS | PM | Test + prod redirect URIs. | Client ID/secret in vault. | OAuth consent screen approved. | E00-S1-T1
E01 | Identity & Subscription Foundation | E01-S2 | Google OAuth (one-tap) | E01-S2-T2 | Add Google provider config | S1 | XS | BE | Wire Google provider into Auth.js v5. | Provider config; login button on signup + login. | OAuth flow returns a usable session. | E01-S2-T1, E01-S1-T1
E01 | Identity & Subscription Foundation | E01-S2 | Google OAuth (one-tap) | E01-S2-T3 | Account-linking on email match | S1 | S | BE | If a Google account email matches an existing User, link Account rather than create a duplicate. | Linking logic + tests. | No duplicate User rows when same email logs in via both providers. | E01-S2-T2
E01 | Identity & Subscription Foundation | E01-S2 | Google OAuth (one-tap) | E01-S2-T4 | E2E for Google flow (mocked) | S1 | S | QA | Mock the OAuth dance in Playwright. | Spec; runs in CI. | Spec green. | E01-S2-T2
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T1 | Prisma Subscription model + migration | S1 | S | BE | Fields: userId, tier (FREE¦WEEKLY¦MONTHLY¦YEARLY), status, provider, providerCustomer, providerSub, currentPeriodEnd, cancelAt. | Migration; client regenerated. | Schema validates; round-trip create/read works. | E01-S1-T2
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T2 | Tier enum + entitlement matrix | S1 | S | BE | Update data/pricing.json (Zod-validated) with the four tiers + per-feature entitlements. | data/pricing.json; Zod schema; tests. | Pricing UI reads from this; no drift. | E01-S3-T1
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T3 | lib/entitlements.ts + useEntitlements() | S1 | S | BE | Typed entitlementsFor(user) returns picksPerDay, valueBets, alerts, kelly, warRoom, telegram, whatsapp, calibrationDepthDays. | Server helper + React hook + tests. | Free user gets 2-3 picks, no value-bets, no Telegram, no Kelly, 30d backtest depth. | E01-S3-T2
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T4 | Replace dashboard hardcoded KPIs | S1 | S | FE | Remove Win Rate 89.3% etc.; wire dashboard to entitlement + UserPick later. | Updated dashboard/page.tsx; visual regression test. | No hardcoded numerics; demo state clearly labeled if shown. | E01-S3-T3
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T5 | Replace Premium 'Unlocked' copy | S1 | S | FE | Tier-aware Premium section reading from entitlements. | Updated section; design QA pass. | Free user sees what they don't have; paid user sees what they do. | E01-S3-T3
E01 | Identity & Subscription Foundation | E01-S3 | Subscription model + entitlement middleware | E01-S3-T6 | Unit tests entitlementsFor() per tier | S1 | S | QA | Cover all four tiers x every feature combo. | Vitest spec. | 100% branch coverage on entitlementsFor. | E01-S3-3
E01 | Identity & Subscription Foundation | E01-S4 | Account & RG settings page | E01-S4-T1 | Account profile page + form | S1 | S | FE | Email, name, locale, region, change password. | /[locale]/account page. | Form save reflected in DB; success toast. | E01-S1-T2
E01 | Identity & Subscription Foundation | E01-S4 | Account & RG settings page | E01-S4-T2 | Sessions list + revoke | S1 | S | BE+FE | List active sessions; revoke individual or all-but-current. | Page section + API. | Revoked session cannot reuse cookie. | E01-S1-T1
E01 | Identity & Subscription Foundation | E01-S4 | Account & RG settings page | E01-S4-T3 | RG flags UI | S1 | M | FE+BE | Self-exclude radio (24h/7d/30d/permanent); cool-off; advisory deposit cap; 18+ reaffirmation. Persist to User.rgFlags; emit rg.selfExclude.start audit event. | UI + API + audit hook. | Setting self-exclude blocks all picks UI immediately. | E01-S1-T6
E01 | Identity & Subscription Foundation | E01-S4 | Account & RG settings page | E01-S4-T4 | Suspended banner | S1 | S | FE | Server-component banner that suppresses all picks UI when rgFlags.selfExcludedUntil > now. | Banner component; integration test. | Suspended user sees banner instead of picks across all pages. | E01-S4-T3
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S1 | Paystack checkout integration (test mode) | E02-S1-T1 | POST /api/billing/checkout (init Paystack) | S1 | S | BE | Tier from query; build Paystack init call; return authorization_url. Store idempotency key. | Route + tests. | Calling twice with same idempotency key returns same auth URL. | E00-S1-T2, E01-S3-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S1 | Paystack checkout integration (test mode) | E02-S1-T2 | /[locale]/billing/checkout UI | S1 | S | FE+DES | Inline-checkout page: plan summary, currency note, redirect. | Page; visual QA. | Tier query parameter respected; mobile-first layout. | E02-S1-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S1 | Paystack checkout integration (test mode) | E02-S1-T3 | Idempotency in KV | S1 | S | BE | Store request ID for 10 min; reject duplicates. | Helper + tests. | Concurrent submissions create only one Paystack session. | E02-S1-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S1 | Paystack checkout integration (test mode) | E02-S1-T4 | billing/thanks page | S1 | S | FE | Reads ?reference query; shows pending/active state until webhook arrives. | Page; polling logic with backoff. | Updates within 30s of webhook delivery. | E02-S1-T2
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S2 | Paystack webhook (canonical source) | E02-S2-T1 | Webhook signature verification | S1 | S | BE | Verify HMAC X-Paystack-Signature using PAYSTACK_SECRET_KEY. | Helper + tests; rejects bad signatures with 401. | Fuzz test: 100 random bodies all rejected. | E00-S1-T2
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S2 | Paystack webhook (canonical source) | E02-S2-T2 | Event router + handlers | S1 | M | BE | Handle: subscription.create, subscription.disable, invoice.create, invoice.payment_failed, charge.success, charge.failed. Idempotent on event.id. | Route + per-event handler; tests. | Replaying the same event 5x does not duplicate state changes. | E02-S2-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S2 | Paystack webhook (canonical source) | E02-S2-T3 | WebhookDelivery row dedup | S1 | S | BE | Persist row keyed on event.id for replay/dedup. AuditLog entry per event. | Model + index; tests. | Inspection query: distinct event IDs across the table. | E02-S2-T2
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S2 | Paystack webhook (canonical source) | E02-S2-T4 | Manual entitlement-fix admin endpoint | S1 | S | BE | Gated to admin role for support ops. | /api/admin/entitlements/[userId] PATCH; audit; rate-limited. | Non-admin returns 403. | E02-S2-T2, E07-S3-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S2 | Paystack webhook (canonical source) | E02-S2-T5 | Webhook replay simulator CLI | S1 | S | BE | Script to POST canned events from a JSON fixture; useful for QA + incident response. | scripts/billing/replay.ts. | Replays a charge.success and updates DB locally. | E02-S2-T2
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S3 | Dunning + cancel-at-period-end | E02-S3-T1 | currentPeriodEnd recomputation | S1 | S | BE | Update from invoice.create. | Handler + tests. | currentPeriodEnd advances on renewal invoice. | E02-S2-T2
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S3 | Dunning + cancel-at-period-end | E02-S3-T2 | Cancel API + UI button | S1 | S | BE+FE | /api/billing/cancel schedules cancellation; UI button on /account/billing. | Route + button + confirmation modal. | User retains entitlement until currentPeriodEnd. | E02-S2-T2, E01-S4-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S3 | Dunning + cancel-at-period-end | E02-S3-T3 | Dunning emails (T+1d/3d/7d) | S1 | S | BE+DES | Resend templates for past_due reminders. | Templates + scheduler. | Each reminder fires once per dunning cycle. | E02-S2-T2, E06-S1-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S3 | Dunning + cancel-at-period-end | E02-S3-T4 | Soft suspend at period end | S1 | S | BE+FE | If unpaid past currentPeriodEnd, downgrade to FREE; banner explains. | Logic + banner. | Once downgraded, paid features hidden; re-subscribing restores tier. | E02-S3-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S4 | Flutterwave fallback (feature-flagged) | E02-S4-T1 | Provider adapter interface | S1 | S | BE | lib/billing/provider.ts defines getCheckoutUrl, verifyWebhook, handlers. | Interface + Paystack impl conforming. | Both adapters compile against the same interface. | E02-S1-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S4 | Flutterwave fallback (feature-flagged) | E02-S4-T2 | Flutterwave adapter (test keys) | S1 | M | BE | Implements the provider interface. | Adapter + tests + docs. | Same end-to-end test passes with BILLING_PROVIDER=flutterwave. | E02-S4-T1
E02 | Payments (Paystack first, Flutterwave fallback) | E02-S4 | Flutterwave fallback (feature-flagged) | E02-S4-T3 | Switch tests for both providers | S1 | S | QA | Run the full billing e2e suite against both providers in CI matrix. | Workflow matrix + green run. | Both columns green. | E02-S4-T2
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T1 | QStash schedule registration script | S2 | S | SRE | scripts/qstash-register.ts idempotently registers schedules for the six workers. | Script; runbook entry. | Schedules visible in Upstash console after one run. | E00-S1-T5
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T2 | fixture-sync worker | S2 | M | BE | Reads FOOTBALL_DATA_COMPETITIONS; 7s jitter between provider calls; idempotent upsert. | /api/workers/fixture-sync + tests + heartbeat. | Two consecutive runs produce zero new rows when data unchanged. | E03-S1-T1
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T3 | odds-ingest worker | S2 | M | BE | Pulls The Odds API for fixtures within 48h; respects rate-limit. | /api/workers/odds-ingest + tests. | Backs off on 429; reports remaining quota. | E03-S1-T1, E00-S1-T4
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T4 | prediction worker | S2 | M | BE+ML | Iterates fixtures lacking snapshot in last 6h; calls model; writes PredictionSnapshot. | /api/workers/prediction + tests. | Covered fixtures get a snapshot within 60 min of cron tick. | E03-S1-T1, E04-S2-T4
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T5 | settlement worker | S2 | S | BE | Fetches finished fixtures; writes FixtureResult; triggers backtest run. | /api/workers/settlement + tests. | Settled fixtures evaluated within 24h. | E03-S1-T1
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T6 | backtest worker | S2 | S | BE | Calls runBacktest(prisma, { windowDays: 90 }). | /api/workers/backtest. | Each run produces a PredictionBacktestRun row + buckets. | E03-S1-T1
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T7 | notify worker (placeholder) | S2 | S | BE | Stub for E06 in S3. | /api/workers/notify returning {ok:true} + heartbeat. | Wires into the schedule. | E03-S1-T1
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T8 | Shared runWorker(name, fn) wrapper | S2 | S | BE | Timing + audit + heartbeat + Sentry capture; standard error envelope. | lib/workers/runWorker.ts + tests. | All workers use it; standardized log shape in Axiom.
E03 | Data Ingestion v2 | E03-S1 | Cron -> QStash worker decomposition | E03-S1-T9 | Remove /api/cron/daily-refresh | S2 | XS | BE | Delete legacy route + vercel.json cron entry. | Commit diff. | Vercel deploy succeeds without cron config. | E03-S1-T2..7
E03 | Data Ingestion v2 | E03-S2 | Secondary fixtures provider | E03-S2-T1 | Provider interface + Football-Data adapter | S2 | S | BE | FixturesProvider interface; primary implementation reuses existing code. | Interface + adapter. | Existing behavior preserved.
E03 | Data Ingestion v2 | E03-S2 | Secondary fixtures provider | E03-S2-T2 | Sportmonks adapter | S2 | M | BE | Implements FixturesProvider on Sportmonks Bronze. | Adapter + tests + coverage notes. | Pulls and normalizes a sample league correctly. | E03-S2-T1, E00-S1-T4
E03 | Data Ingestion v2 | E03-S2 | Secondary fixtures provider | E03-S2-T3 | Failover state machine | S2 | S | BE | 3 consecutive 4xx/5xx -> switch; 30-min cool-down before retrying primary. | lib/providers/failover.ts + tests. | Synthetic outage triggers switch within 3 calls. | E03-S2-T2
E03 | Data Ingestion v2 | E03-S2 | Secondary fixtures provider | E03-S2-T4 | Failover runbook | S2 | S | SRE | docs/runbooks/provider-failover.md. | Doc committed. | Reviewed by on-call SRE. | E03-S2-T3
E03 | Data Ingestion v2 | E03-S3 | Aggregated bookmaker odds | E03-S3-T1 | The Odds API adapter | S2 | M | BE | Map bookmakers.key -> our bookCode (sportybet, bet9ja, onexbet, betking, msport, pinnacle). | Adapter + mapping table + tests. | Sample fixture lists odds from >=3 bookcodes when API returns them. | E00-S1-T4
E03 | Data Ingestion v2 | E03-S3 | Aggregated bookmaker odds | E03-S3-T2 | Admin CSV upload for NPFL | S2 | M | BE | /api/admin/odds/upload accepting CSV; validates schema; idempotent. | Route + Zod schema + tests. | Re-uploading same CSV does not duplicate rows. | E07-S3-T1
E03 | Data Ingestion v2 | E03-S3 | Aggregated bookmaker odds | E03-S3-T3 | Remove MODEL fair-price odds | S2 | S | BE+ML | Migration deletes legacy bookCode='MODEL' rows; model gracefully returns valueBet=false when no real odds present. | Migration + code change + tests. | After migration, zero MODEL rows; predictions still produced. | E03-S3-T1, E04-S2-T5
E03 | Data Ingestion v2 | E03-S3 | Aggregated bookmaker odds | E03-S3-T4 | Tests for Odds API mapping | S2 | S | QA | Unit + integration with recorded fixtures. | Spec. | All bookmaker mappings verified. | E03-S3-T1
E03 | Data Ingestion v2 | E03-S4 | Enrichment: weather + injuries | E03-S4-T1 | FixtureEnrichment model | S2 | XS | BE | Stores weatherJson, injuriesJson, refereeJson, capturedAt. | Migration. | Schema validates.
E03 | Data Ingestion v2 | E03-S4 | Enrichment: weather + injuries | E03-S4-T2 | OpenWeather adapter | S2 | S | BE | Kickoff venue if available; one-off cached per fixture. | Adapter + tests. | Returns valid forecast; failure handled gracefully. | E03-S4-T1, E00-S1-T4
E03 | Data Ingestion v2 | E03-S4 | Enrichment: weather + injuries | E03-S4-T3 | Injury feed adapter | S2 | M | BE | RotoWire-lite or curated JSON; impact-weighted. | Adapter + tests. | Returns impact-weighted injury list per team. | E03-S4-T1
E03 | Data Ingestion v2 | E03-S4 | Enrichment: weather + injuries | E03-S4-T4 | Narrative generator updated | S2 | S | BE | Surface weather/injury when material (wind > 20 km/h, >=2 starting-XI injuries either side). | Updated narrative; tests. | Sample fixtures with material conditions get enriched narratives. | E03-S4-T2, E03-S4-T3
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T1 | packages/ml sub-workspace + tooling | S2 | S | ML | Python sub-workspace; uv/poetry config; pre-commit; ruff + mypy. | Sub-workspace skeleton. | uv run pytest passes.
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T2 | Elo with home edge + competition-strength | S2 | M | ML | K=20, home edge 60; competition-strength normalization. | Module + unit tests. | Backtest Elo alone beats a coin flip in covered leagues. | E04-S1-T1
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T3 | Dixon-Coles bivariate Poisson | S2 | M | ML | Rolling 365-day fit; time-decay parameter exposed. | Module + tests. | Fitted params stored versioned in R2. | E04-S1-T2
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T4 | Recent-form features (5/10) | S2 | M | ML | SoS-adjusted; null-safe. | Module + tests. | Features non-null for every covered fixture with >=5 history. | E04-S1-T1
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T5 | Injury / weather / referee feature extractors | S2 | M | ML | Pull from FixtureEnrichment; impact-weight. | Module + tests. | Features exported for every fixture where enrichment exists. | E03-S4-T3
E04 | Prediction Engine v2 | E04-S1 | Feature pipeline | E04-S1-T6 | Write FixtureFeatures via Prisma | S2 | S | ML+BE | Use prisma-client-py OR ingest API route. | Pipeline writes a FixtureFeatures row per fixture. | Roundtrip verified. | E04-S1-T4
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T1 | Time-based train/test split (no leakage) | S2 | S | ML | 80/20 by date; document seed. | Notebook + saved indices. | Repro run yields same split. | E04-S1-T6
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T2 | XGBoost training + Platt calibration | S2 | M | ML | 1X2, O/U 2.5, BTTS labels. Platt scaling for calibration. | Trained model + metrics report. | Brier < 0.21 on held-out test; calibration error < 0.05. | E04-S2-T1
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T3 | Model versioning in R2 | S2 | S | ML+SRE | models/v<semver>/model.pkl; MODEL_VERSION env points to active. | Pickle in R2; pointer env var. | Switching MODEL_VERSION swaps the served model with zero downtime. | E04-S2-T2, E00-S1-T5
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T4 | Serving endpoint (Modal or Vercel Edge) | S2 | M | ML+BE | Stateless; returns {probabilities, drivers[]}. | Endpoint URL + auth; tests. | p95 < 200ms warm. | E04-S2-T3
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T5 | Prediction worker calls remote endpoint | S2 | S | BE | Replace lib/prediction-engine/model.ts call with HTTP call. | Updated worker; fallback to local model if remote unreachable + Sentry warning. | Fallback covered by integration test. | E04-S2-T4, E03-S1-T4
E04 | Prediction Engine v2 | E04-S2 | Train + serve XGBoost | E04-S2-T6 | Keep local model.ts as fallback | S2 | S | BE | Preserve existing model for offline / outage. | Doc note + tests. | Fallback used when remote 5xxs 3x. | E04-S2-T5
E04 | Prediction Engine v2 | E04-S3 | Calibration & evaluation surfaced | E04-S3-T1 | Server-render methodology from live data | S2 | S | FE+BE | Latest PredictionBacktestRun + PredictionCalibrationBucket rendered. | Updated page; ISR 1h. | Numbers match DB exactly. | E03-S1-T6
E04 | Prediction Engine v2 | E04-S3 | Calibration & evaluation surfaced | E04-S3-T2 | Calibration plot component | S2 | M | FE | Recharts/D3 line: predicted vs. observed with confidence bands. | Component + Storybook entry. | Renders correctly across 3 device profiles. | E04-S3-T1
E04 | Prediction Engine v2 | E04-S3 | Calibration & evaluation surfaced | E04-S3-T3 | Per-bucket hit-rate table | S2 | S | FE | Bucket label, n, predicted, observed, error. | Component. | Sortable; loads in < 100ms. | E04-S3-T1
E04 | Prediction Engine v2 | E04-S3 | Calibration & evaluation surfaced | E04-S3-T4 | Repositioning copy pass on methodology | S2 | S | DES+PM | Remove win-rate language; install calibrated-probability + edge language per repositioning doc. | Copy diff; legal review. | Forbidden phrases absent (rg check). | E04-S3-T1
E04 | Prediction Engine v2 | E04-S4 | Multi-market (O/U + BTTS) | E04-S4-T1 | Widen market enum + migration | S2 | S | BE | Add O25_OVER, O25_UNDER, BTTS_YES, BTTS_NO. | Migration; type refresh. | Existing rows untouched.
E04 | Prediction Engine v2 | E04-S4 | Multi-market (O/U + BTTS) | E04-S4-T2 | Model output extended | S2 | M | ML | Serving endpoint contract returns per-market probabilities. | Endpoint update + tests. | Roundtrip serialisation OK. | E04-S4-T1, E04-S2-T4
E04 | Prediction Engine v2 | E04-S4 | Multi-market (O/U + BTTS) | E04-S4-T3 | Match-detail multi-market UI | S2 | M | FE | Multi-market table with edge per market. | Component + tests. | Renders all 7 markets for sample fixture. | E04-S4-T2
E05 | Product UX | E05-S1 | Onboarding (4 steps) | E05-S1-T1 | /[locale]/onboarding/[step] wizard | S3 | M | FE+DES | Pick leagues -> notification prefs -> region -> first 3 picks. | Wizard pages + state machine. | User completes flow; analytics fires for each step. | E01-S1-T1
E05 | Product UX | E05-S1 | Onboarding (4 steps) | E05-S1-T2 | User.preferences Json + API | S3 | S | BE | Persist user prefs. | Migration + API. | Round-trip via UI. | E05-S1-T1
E05 | Product UX | E05-S1 | Onboarding (4 steps) | E05-S1-T3 | Picks recommendation reads preferences | S3 | S | BE | Predictions feed filtered by user.preferences.leagues. | Server helper + tests. | Sample user sees only their preferred leagues by default. | E05-S1-T2
E05 | Product UX | E05-S1 | Onboarding (4 steps) | E05-S1-T4 | Onboarding analytics in PostHog | S3 | S | FE | Event per step + funnel report. | Funnel saved in PostHog. | Funnel populated within 24h. | E05-S1-T1, E00-S1-T5
E05 | Product UX | E05-S2 | Dashboard rewrite (real per-user) | E05-S2-T1 | UserPick model + migration | S3 | S | BE | Track user picks; settlements; P&L. | Migration. | Schema validates.
E05 | Product UX | E05-S2 | Dashboard rewrite (real per-user) | E05-S2-T2 | Pick CRUD + auto-settle | S3 | M | BE | POST /api/picks; POST /api/picks/[id]/settle (manual override); auto-settle on FixtureResult.upsert. | Routes + helper + tests. | Settled picks reflect outcome within 5 min of fixture finishing. | E05-S2-T1
E05 | Product UX | E05-S2 | Dashboard rewrite (real per-user) | E05-S2-T3 | Dashboard UI rewrite | S3 | M | FE | KPIs from UserPick joined to PredictionEvaluation. Real numbers only. | Page. | No hardcoded numerics; demo banner removed. | E05-S2-T2, E01-S3-T4
E05 | Product UX | E05-S2 | Dashboard rewrite (real per-user) | E05-S2-T4 | Per-user backtest tile | S3 | S | BE+FE | Tile shows user's rolling 30d ROI, hit-rate, Brier. | Component. | Numbers match a hand-spot-check against DB. | E05-S2-T2
E05 | Product UX | E05-S3 | Match detail rewrite | E05-S3-T1 | Design + Figma handoff | S3 | M | DES | Live odds across NG books, edge per market, calibrated confidence, Kelly (Pro), narrative. | Figma file + redlines. | Approved by PM.
E05 | Product UX | E05-S3 | Match detail rewrite | E05-S3-T2 | Server component fetching all data | S3 | M | FE+BE | Fixture + enrichment + odds + snapshot. | Page. | TTFB < 600ms. | E04-S4-T2, E03-S3-T1, E03-S4-T2
E05 | Product UX | E05-S3 | Match detail rewrite | E05-S3-T3 | Value-bet chip + tooltip | S3 | S | FE | Explains edge. | Component + tests. | Tooltip accessible; keyboard-navigable. | E05-S3-T2
E05 | Product UX | E05-S3 | Match detail rewrite | E05-S3-T4 | Kelly stake calculator (Pro) | S3 | S | FE | Quarter Kelly stake given bankroll + confidence. | Component; entitlement-gated. | Numbers match a separate spreadsheet check. | E01-S3-T3
E05 | Product UX | E05-S3 | Match detail rewrite | E05-S3-T5 | Bookmaker deeplink with affiliate UTM | S3 | S | BE+FE | Outbound link with affiliateUrlTemplate + tracking. | Component + AffiliateClick logging. | Click writes AffiliateClick row. | E05-S5-T2
E05 | Product UX | E05-S4 | Referral funnel | E05-S4-T1 | Wire referralToken into User | S3 | S | BE | Copy field from WaitlistSignup to User on signup. | Migration + code. | New users have a unique token. | E01-S1-T2
E05 | Product UX | E05-S4 | Referral funnel | E05-S4-T2 | Reward grant job | S3 | S | BE | On user.verifiedAt, if referredByToken within 30d window, grant 7-day Edge Weekly to referrer. | Worker hook + tests. | Grant idempotent; cap at 12/year per referrer. | E05-S4-T1, E02-S2-T2
E05 | Product UX | E05-S4 | Referral funnel | E05-S4-T3 | Referrals UI page | S3 | S | FE+DES | /account/referrals shows token, share link, totals. | Page. | Shareable WhatsApp link prefilled in NG locale. | E05-S4-T1
E05 | Product UX | E05-S5 | Bookmakers data + affiliate tracking | E05-S5-T1 | Bookmaker model + seed | S3 | S | BE | Replace bookmakers.json with DB-backed Bookmaker table. | Migration + seed. | Existing UI reads from DB.
E05 | Product UX | E05-S5 | Bookmakers data + affiliate tracking | E05-S5-T2 | AffiliateClick + GO redirect | S3 | S | BE | GET /go/<bookCode>?fixtureId=&market= redirects with affiliate UTM and writes click. | Route + model + tests. | Click record stored; hashed IP/UA. | E05-S5-T1
E05 | Product UX | E05-S5 | Bookmakers data + affiliate tracking | E05-S5-T3 | Affiliate reconciliation script | S3 | M | BE | Weekly compare our ledger vs. affiliate exports. | Script + report template. | Discrepancies surfaced > 5% trigger an alert. | E05-S5-T2
E06 | Notifications | E06-S1 | Email digest | E06-S1-T1 | Resend daily-digest template | S3 | S | DES+BE | React Email template; top picks for next 36h. | Template; preview deploy. | Renders correctly in Gmail + Outlook + iOS Mail. | E00-S1-T1
E06 | Notifications | E06-S1 | Email digest | E06-S1-T2 | notify worker 05:30 UTC tick | S3 | M | BE | Iterate subscribed users; send digest. | Worker logic; tests. | Batch of 1k users sends in < 5 min. | E03-S1-T7, E06-S1-T1
E06 | Notifications | E06-S1 | Email digest | E06-S1-T3 | Unsubscribe handler + preferences page | S3 | S | BE+FE | Resend unsubscribe + granular prefs. | Page + route. | Unsubscribed user removed from next digest. | E01-S4-T1
E06 | Notifications | E06-S1 | Email digest | E06-S1-T4 | Bounce / complaint webhook | S3 | S | BE | Suppress further sends on bounce/complaint. | Route + suppression list. | Synthetic bounce suppresses next send. | E06-S1-T2
E06 | Notifications | E06-S2 | Telegram bot | E06-S2-T1 | Register bot, capture token | S3 | XS | PM | @ApexPredictNG channel + bot. | Token in vault. | Bot answers /start.
E06 | Notifications | E06-S2 | Telegram bot | E06-S2-T2 | Channel post on schedule | S3 | S | BE | Posts 2 free picks at 07:00 WAT. | Worker job. | Test post visible at scheduled time. | E06-S2-T1, E03-S1-T7
E06 | Notifications | E06-S2 | Telegram bot | E06-S2-T3 | Pro user linking flow | S3 | M | BE | /start <linkToken> binds chatId to user. | Flow + tests. | Linked user receives DMs. | E06-S2-T1, E01-S1-T1
E06 | Notifications | E06-S2 | Telegram bot | E06-S2-T4 | Value-bet alert DM | S3 | S | BE | When prediction worker flags edge >= 3% in next 6h. | Alert worker + opt-out. | Pro user receives DM within 60s of flag. | E06-S2-T3, E03-S1-T4
E06 | Notifications | E06-S3 | WhatsApp Business (v1.1 stub) | E06-S3-T1 | Profile field + UI | S3 | XS | FE | Collect opt-in. | Field + UI. | Persists.
E06 | Notifications | E06-S3 | WhatsApp Business (v1.1 stub) | E06-S3-T2 | Persist opt-in audit event | S3 | XS | BE | AuditLog entry. | Code. | Event appears for sample user. | E01-S1-T6
E07 | Compliance & Responsible Gaming | E07-S1 | KYC at Pro signup (Smile ID) | E07-S1-T1 | Smile ID server SDK integration | S4 | M | BE | Verify NIN/BVN/DL/Voters Card. Sandbox first then prod. | Adapter + tests; audit events. | Pass/fail callback wired. | E00-S1-T3
E07 | Compliance & Responsible Gaming | E07-S1 | KYC at Pro signup (Smile ID) | E07-S1-T2 | KYC modal UI | S4 | M | FE+DES | Triggered when starting an Edge subscription. | Modal + flow. | Pro entitlement blocked until verified. | E07-S1-T1
E07 | Compliance & Responsible Gaming | E07-S1 | KYC at Pro signup (Smile ID) | E07-S1-T3 | Manual review admin queue | S4 | M | BE+FE | Admin-only page to approve/deny edge cases. | Page + actions; audit. | Decisions persisted; user notified. | E07-S1-T1, E02-S2-T4
E07 | Compliance & Responsible Gaming | E07-S1 | KYC at Pro signup (Smile ID) | E07-S1-T4 | Audit + Sentry on outcomes | S4 | S | BE | Every KYC outcome logged. | Wired into helper. | Audit visible to compliance. | E01-S1-T6
E07 | Compliance & Responsible Gaming | E07-S2 | Self-exclusion (functional) | E07-S2-T1 | Suspended middleware + hook | S4 | S | BE+FE | useSuspended() client + middleware server. | Code + tests. | Suspended user blocked from /predictions, /dashboard, /match. | E01-S4-T3
E07 | Compliance & Responsible Gaming | E07-S2 | Self-exclusion (functional) | E07-S2-T2 | Email + Telegram suppression | S4 | S | BE | notify worker suppresses for suspended users. | Code + tests. | Suspended user receives zero notifications during window. | E06-S1-T2, E06-S2-T4
E07 | Compliance & Responsible Gaming | E07-S2 | Self-exclusion (functional) | E07-S2-T3 | Locked confirmation modal + legal copy | S4 | S | FE+DES+Counsel | Reaffirm before activating; explain irreversibility within window. | Modal + copy review. | Counsel signs off. | E01-S4-T3
E07 | Compliance & Responsible Gaming | E07-S3 | Audit log immutable | E07-S3-T1 | Neon role split | S4 | S | SRE+BE | Roles: app_rw, app_ro, app_admin, auditor. | Role grants; rotated keys. | app_rw cannot UPDATE/DELETE AuditLog.
E07 | Compliance & Responsible Gaming | E07-S3 | Audit log immutable | E07-S3-T2 | RLS policies on user-scoped tables | S4 | M | BE | User, Subscription, UserPick, AuditLog, AffiliateClick. | Policies + tests. | User A cannot read User B rows in any user-scoped table. | E07-S3-T1
E07 | Compliance & Responsible Gaming | E07-S3 | Audit log immutable | E07-S3-T3 | Quarterly cold export to R2 | S4 | S | SRE | Sealed exports. | Job + cold bucket. | First export round-trip verified. | E07-S3-T1
E07 | Compliance & Responsible Gaming | E07-S4 | Cookie consent v2 | E07-S4-T1 | Increment CONSENT_VERSION | S4 | XS | FE+BE | Force re-banner on bump. | Constant + migration. | All users see fresh banner.
E07 | Compliance & Responsible Gaming | E07-S4 | Cookie consent v2 | E07-S4-T2 | Update legal mdx | S4 | S | Counsel+FE | Privacy / Terms / Cookies refreshed. | MDX diff; legal sign-off. | Public legal pages re-rendered. | E00-S3-T1
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T1 | Route catalog + URL helpers | S3 | S | FE | lib/seo/routes.ts. | Module + tests. | URLs match the schema; round-trip parse.
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T2 | /free-tips/[league]/[date] | S3 | M | FE+BE | ISR 1h; SEO meta + JSON-LD SportsEvent. | Page + tests. | 100 sample dates render correctly; no soft-404. | E08-S1-T1
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T3 | /team/[slug] | S3 | M | FE | Form, last 5, calibration history. | Page. | Sample teams render. | E08-S1-T1
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T4 | /h2h/[a]-vs-[b] | S3 | M | FE | H2H history. | Page. | Sample H2H renders. | E08-S1-T1
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T5 | /competition/[slug]/predictions and /table | S3 | M | FE | League hub pages. | Pages. | Sample league pages render. | E08-S1-T1
E08 | SEO & Content | E08-S1 | Programmatic leaf pages | E08-S1-T6 | No-data fallback per page | S3 | S | FE | Avoid soft-404 when no fixtures. | Component. | Returns 200 with helpful copy.
E08 | SEO & Content | E08-S2 | DB-driven sitemap + hreflang | E08-S2-T1 | DB-driven sitemap.ts | S3 | S | BE | Enumerate every leaf URL with lastmod. | Updated sitemap. | XML validates; lastmod present per row. | E08-S1-T2..5
E08 | SEO & Content | E08-S2 | DB-driven sitemap + hreflang | E08-S2-T2 | hreflang injector | S3 | S | FE | Add hreflang + x-default on multi-locale pages. | Updated layout. | Validator passes.
E08 | SEO & Content | E08-S2 | DB-driven sitemap + hreflang | E08-S2-T3 | GSC submit + validate | S3 | S | PM | Submit sitemap to Search Console. | Screenshot evidence. | Structured-data errors = 0. | E08-S2-T1
E08 | SEO & Content | E08-S3 | Blog scaffold + first 6 posts | E08-S3-T1 | MDX content pipeline | S3 | S | FE | Frontmatter schema; rendering. | Code. | Sample post renders.
E08 | SEO & Content | E08-S3 | Blog scaffold + first 6 posts | E08-S3-T2 | Blog list + detail pages | S3 | S | FE+DES | Cards on list; full post on detail. | Pages. | Accessibility audit passes. | E08-S3-T1
E08 | SEO & Content | E08-S3 | Blog scaffold + first 6 posts | E08-S3-T3 | Author 6 launch posts (EN) | S3 | XL | PM | NPFL guide, accuracy method, value-bet 101, bankroll discipline, AFCON preview, PL opening weekend. | 6 MDX files. | Counsel sign-off on copy. | E08-S3-T2
E09 | Security & Reliability | E09-S1 | RLS on Neon | E09-S1-T1 | Enable RLS on user-scoped tables | S4 | M | BE+SRE | User, Subscription, UserPick, AuditLog, AffiliateClick. | Policies. | RLS enforced in pg_authid. | E07-S3-T1
E09 | Security & Reliability | E09-S1 | RLS on Neon | E09-S1-T2 | lib/db/auth-context.ts | S4 | S | BE | Set auth.uid() per request. | Helper + tests. | All Prisma queries scoped by uid. | E09-S1-T1
E09 | Security & Reliability | E09-S1 | RLS on Neon | E09-S1-T3 | RLS integration tests | S4 | S | QA | tests/security/rls.spec.ts. | Spec. | Negative tests all return 0 rows. | E09-S1-T2
E09 | Security & Reliability | E09-S2 | WAF rules + bot management | E09-S2-T1 | Author cf-rules.json | S4 | S | SRE | Rules for /api/auth/*, /api/billing/*, /api/waitlist. | Rules file. | Lints clean.
E09 | Security & Reliability | E09-S2 | WAF rules + bot management | E09-S2-T2 | Apply rules via API + Terraform | S4 | M | SRE | tf/cloudflare module. | tf plan/apply. | Rules visible in CF dashboard. | E09-S2-T1
E09 | Security & Reliability | E09-S2 | WAF rules + bot management | E09-S2-T3 | Synthetic abuse tests | S4 | S | SRE | Verify rate-limit kicks in. | Script. | 100 RPS spike triggers 429s after threshold. | E09-S2-T2
E09 | Security & Reliability | E09-S3 | External penetration test | E09-S3-T1 | RFP + scope | S4 | S | PM | Scope: black-box + grey-box. | RFP + signed SOW. | Engagement booked.
E09 | Security & Reliability | E09-S3 | External penetration test | E09-S3-T2 | Engagement window booked | S4 | XS | PM | Week 7. | Calendar event. | Pen-test starts on schedule. | E09-S3-T1
E09 | Security & Reliability | E09-S3 | External penetration test | E09-S3-T3 | Remediation sprint | S4 | XL | BE+SRE | Fix all high/critical findings before launch. | PRs; retest evidence. | Final report shows no open high/critical. | E09-S3-T2
E09 | Security & Reliability | E09-S4 | Load test (k6) | E09-S4-T1 | k6 script | S4 | S | SRE | 5k concurrent + 50 RPS sustained, 30 min, landing + predictions + match + waitlist. | Script in tests/load. | Script runs locally.
E09 | Security & Reliability | E09-S4 | Load test (k6) | E09-S4-T2 | Run on staging; report | S4 | S | SRE | Execute and capture metrics. | Report. | error_rate < 0.5%; p95 < 800ms. | E09-S4-T1
E09 | Security & Reliability | E09-S4 | Load test (k6) | E09-S4-T3 | Resolve bottlenecks | S4 | M | BE+SRE | DB pool, ISR tuning, etc. | PRs. | Targets met. | E09-S4-T2
E09 | Security & Reliability | E09-S5 | Status page + runbooks | E09-S5-T1 | Stand up status page | S4 | S | SRE | Statuspage Hobby or Better Uptime. | Page live. | Components defined.
E09 | Security & Reliability | E09-S5 | Status page + runbooks | E09-S5-T2 | Sentry error-budget hook | S4 | M | SRE | Auto-flip component to Degraded. | Webhook + tests. | Synthetic alert flips component within 2 min. | E09-S5-T1
E09 | Security & Reliability | E09-S5 | Status page + runbooks | E09-S5-T3 | 7 incident runbooks | S4 | M | SRE | Provider outage, payment outage, KYC outage, DB failover, deploy rollback, KV outage, Sentry outage. | docs/runbooks/*.md. | Each reviewed by on-call SRE.
E10 | Launch & GTM | E10-S1 | Soft launch (1,000 closed beta) | E10-S1-T1 | Beta-invite mailer + tracking | S4/Launch | S | BE+DES | Wave 1: 1,000 users from waitlist; tracked. | Mailer + dashboard. | Open + signup rates visible. | E01-S1-T3
E10 | Launch & GTM | E10-S1 | Soft launch (1,000 closed beta) | E10-S1-T2 | Daily funnel report | S4/Launch | S | PM | signup -> verify -> onboarding -> first-pick -> paid. | PostHog funnel. | Reported in daily standup. | E05-S1-T4
E10 | Launch & GTM | E10-S1 | Soft launch (1,000 closed beta) | E10-S1-T3 | Bug-bash schedule + triage | S4/Launch | S | QA | Daily 2-hour bug bash; triage owner. | Schedule. | Backlog burndown.
E10 | Launch & GTM | E10-S2 | PR placements | E10-S2-T1 | Press kit | S4/Launch | S | PM+DES | One-pager + screenshots + CEO quote. | PDF + assets. | Approved by CTO.
E10 | Launch & GTM | E10-S2 | PR placements | E10-S2-T2 | Outreach to 4 publications | S4/Launch | S | PM | Punch, BusinessDay, TechCabal, Techpoint. | Outreach log. | At least 2 confirmed pieces. | E10-S2-T1
E10 | Launch & GTM | E10-S2 | PR placements | E10-S2-T3 | Embargo + go-live coordination | S4/Launch | S | PM | Coordinated launch day messaging. | Comms plan. | Stories appear on or +1 day. | E10-S2-T2
E10 | Launch & GTM | E10-S3 | Affiliate setup | E10-S3-T1 | Affiliate outreach + sign-off | S4/Launch | XL | PM | Sign at least 2 of {SportyBet, Bet9ja, 1xBet, BetKing, MSport}. | Signed agreements. | Tracking codes received.
E10 | Launch & GTM | E10-S3 | Affiliate setup | E10-S3-T2 | Wire tracking codes into Bookmaker rows | S4/Launch | S | BE | Update DB seed with affiliate codes. | Migration + seed. | Outbound links route through codes. | E10-S3-T1, E05-S5-T1
E10 | Launch & GTM | E10-S4 | Support runbook + helpdesk | E10-S4-T1 | Chat widget integration | S4/Launch | S | FE | Crisp/Intercom free. | Widget on site. | Sample message delivered to ops mailbox.
E10 | Launch & GTM | E10-S4 | Support runbook + helpdesk | E10-S4-T2 | Tier-1 support runbook | S4/Launch | S | PM | Top 10 expected questions + escalation flow. | docs/runbooks/support.md. | Reviewed by ops.

## EpicSummary
Epic ID | Epic Name | Stories (count) | Tasks (count) | XS | S | M | L | XL | Approx. effort
E00 | Prep & Foundations | 4 | 22 | 8 | 13 | 1 | 0 | 0 | ~18 dev-days
E01 | Identity & Subscription Foundation | 4 | 21 | 2 | 15 | 4 | 0 | 0 | ~28 dev-days
E02 | Payments (Paystack first, Flutterwave fallback) | 4 | 16 | 0 | 14 | 2 | 0 | 0 | ~20 dev-days
E03 | Data Ingestion v2 | 4 | 21 | 2 | 12 | 7 | 0 | 0 | ~34 dev-days
E04 | Prediction Engine v2 | 4 | 19 | 0 | 10 | 9 | 0 | 0 | ~37 dev-days
E05 | Product UX | 5 | 19 | 0 | 13 | 6 | 0 | 0 | ~31 dev-days
E06 | Notifications | 3 | 10 | 3 | 5 | 2 | 0 | 0 | ~12 dev-days
E07 | Compliance & Responsible Gaming | 4 | 12 | 1 | 7 | 4 | 0 | 0 | ~19 dev-days
E08 | SEO & Content | 3 | 12 | 0 | 7 | 4 | 0 | 1 | ~29 dev-days
E09 | Security & Reliability | 5 | 15 | 1 | 8 | 5 | 0 | 1 | ~33 dev-days
E10 | Launch & GTM | 4 | 10 | 0 | 9 | 0 | 0 | 1 | ~19 dev-days
TOTAL | All epics | 44 | 177 | 17 | 113 | 44 | 0 | 3

## SprintCapacity
Sprint | Window | Theme | XS | S | M | L | XL | Dev-days | Capacity (dev-days) | Capacity OK?
S0 | Fri 2026-06-05 → Mon 2026-06-08 | Kickoff & foundations | 8 | 13 | 1 | 0 | 0 | 18 | 20 | OK
S1 | Tue 2026-06-09 → Mon 2026-06-22 | Identity + Subscription + Payments | 2 | 29 | 6 | 0 | 0 | 47.5 | 60 | OK
S2 | Tue 2026-06-23 → Mon 2026-07-06 | Data ingestion v2 + Prediction v2 | 2 | 22 | 16 | 0 | 0 | 70.5 | 50 | OVERBOOKED
S3 | Tue 2026-07-07 → Mon 2026-07-20 | Product UX + Notifications + SEO | 3 | 25 | 12 | 0 | 1 | 71.75 | 60 | OVERBOOKED
S4 | Tue 2026-07-21 → Mon 2026-08-03 | Compliance, hardening, soft launch | 2 | 15 | 9 | 0 | 1 | 52.5 | 60 | OK
S4/Launch | Tue 2026-08-04 → | Public launch + GTM | 0 | 9 | 0 | 0 | 1 | 19 | 30 | OK

## Legend
Item | Meaning
XS | ≤ 2 hours of focused work
S | ≤ 1 day
M | ≤ 3 days
L | ≤ 5 days
XL | 1-2 weeks
S0 | Pre-kickoff prep — Fri 2026-06-05 → Mon 2026-06-08
S1 | Sprint 1 — Tue 2026-06-09 → Mon 2026-06-22
S2 | Sprint 2 — Tue 2026-06-23 → Mon 2026-07-06
S3 | Sprint 3 — Tue 2026-07-07 → Mon 2026-07-20
S4 | Sprint 4 — Tue 2026-07-21 → Mon 2026-08-03
S4/Launch | Public launch + GTM — Tue 2026-08-04
BE | Backend engineer
FE | Frontend engineer
ML | Machine-learning engineer
SRE | Site reliability / DevSecOps
QA | QA + test automation
PM | Product / project management
DES | Design + copy
Counsel | External legal counsel
DPO | Data Protection Officer